Statement of Work

J&M Employee Time Clock Mobile App — Phase 1

Prepared for: Jed  |  Prepared by: Ben  |  August 2026

# 1. Project Overview

Build a mobile time clock application for iOS and Android that lets employees clock in and out, view tracked hours, see pay information, and receive shift notifications, with a clean, simple interface. The app will connect to the existing backend infrastructure rather than replacing it.

# 2. Existing Infrastructure (Current Tech Stack)

- PostgreSQL database with a working API layer already in place

- Hosted on Azure, with Cloudflare in front handling DNS routing, CDN caching, and security (this is the "routing" piece)

- API keys locked down behind Azure sign-in (Microsoft Entra ID) — the mobile app will authenticate the same way

- Website already live with functioning AI features communicating with the API

- Task tracking: every assignment and feature will be logged as a Jira ticket

- Source control: GitHub repositories connected to VS Code

# 3. Platform Comparison: React Native vs. Native (Swift + Kotlin)

| Criteria | React Native (Expo) | Native Swift + Kotlin |
| --- | --- | --- |
| Codebases to maintain | One shared codebase for iOS and Android | Two separate codebases (Swift for iOS, Kotlin for Android) |
| Development speed | Faster — features built once, shipped to both platforms | Slower — every feature built and tested twice |
| Team required | 1 JavaScript/React developer can cover both platforms | Ideally 1 iOS developer + 1 Android developer (or one dev who knows both) |
| Estimated cost impact | Roughly 40-50% less total effort for the same feature set | Highest cost — near-duplicate effort per platform |
| Performance | Excellent for business apps (forms, lists, clock in/out); not a game engine | Best possible performance and closest access to new OS features |
| Push notifications | Fully supported (Expo Notifications / Firebase / APNs) | Fully supported natively |
| App Store / Play Store | Fully supported; Expo EAS automates builds and store submission | Fully supported; builds managed manually in Xcode / Android Studio |
| Backend fit | Works cleanly with the existing Postgres API over HTTPS | Works cleanly with the existing Postgres API over HTTPS |
| Long-term maintenance | One codebase to patch, test, and update | Every fix and OS update handled twice |
| Best when | Business apps where speed, budget, and one team matter | Apps needing heavy graphics, AR, or deep OS integration |

Recommendation: React Native with Expo and EAS builds. For a business app of this type, it delivers the same end result on both platforms at roughly half the build and maintenance cost, and store submission is fully supported. Note on repositories: with React Native, a single repository serves both platforms; separate "android" and "apple" repos are only necessary if the native Swift + Kotlin route is chosen.

# 4. Frontend Strategy

- Framework: React Native with Expo; EAS for cloud builds and store submission

- Design sequence: user flow diagrams, then wireframes, then high-fidelity Figma mockups, then build — catches logic gaps before code

- Screens (Phase 1): sign in (Azure), clock in/out home, timesheet/history, pay summary, notification preferences

- Authentication: Microsoft MSAL library for Azure sign-in; tokens stored securely on device

- Offline safety: punches queue locally and sync when connection returns

# 5. Backend Strategy

- Extend the existing Postgres API — no new backend platform needed

- New endpoints: create/read time entries, timesheet aggregation by pay period, pay summary

- Pay calculation rules (overtime, rounding, pay periods) defined early with Jed even if some are deferred, to avoid rework

- All traffic continues through Cloudflare to Azure over HTTPS; API access stays gated behind Azure auth

- Admin dashboard planned in architecture now, built in Phase 2

# 6. Phase 1 Scope and Hour Estimates

| Work Item | Notes | Hours |
| --- | --- | --- |
| Project setup: repos, environments, CI/EAS build pipeline | GitHub repos, VS Code workspace, Expo project scaffolding, dev/staging config | 12 |
| Authentication (Azure sign-in) | Microsoft Entra ID (Azure AD) login via MSAL; secure token storage; API keys stay locked behind Azure auth as-is | 20 |
| Clock in / clock out | Core punch flow, timestamps, offline-safe retry, confirmation states | 24 |
| Hours tracking views | Daily/weekly timesheet, pay-period totals, history | 20 |
| Pay display | Read-only earnings view driven by backend pay rules | 12 |
| Shift notifications | Push notification setup (APNs + FCM via Expo), shift reminders, missed-punch alerts | 16 |
| Backend API endpoints | Time entry create/read, timesheet aggregation, pay summary endpoints on existing Postgres API | 24 |
| API integration layer (app side) | Typed API client, error handling, loading states | 12 |
| UI polish and clean design pass | Consistent components, branding, accessibility basics | 16 |
| QA and device testing | iPhone + Android test matrix, edge cases (timezone, DST, offline) | 20 |
| Punch correction requests | Employee submits a fix for a missed or wrong punch; Jed or Mike approves in-app; every edit is logged for a clean audit trail | 14 |
| Break tracking | Separate break punch in/out with unpaid-break deduction — built to whatever break rules Jed confirms | 10 |
| Store preparation and submission | App Store + Play Store listings, screenshots, review process, EAS submit | 12 |
| Total — Phase 1 |  | 212 |

Estimated total: ~212 hours (approximately 6-7 weeks for one full-time developer, or 4-5 weeks with frontend and backend work running in parallel).

# 7. Team / Phases Needed

| Role | Responsibility in Phase 1 | Needed? |
| --- | --- | --- |
| App developer (React Native) | Builds all mobile screens and logic for iOS and Android from one codebase | Yes — core |
| Backend developer | Adds time-entry and pay endpoints to the existing Postgres API; Azure auth wiring | Yes — core |
| UI/UX designer | Wireframes and high-fidelity mockups before build (Figma) | Yes — front-loaded |
| QA tester | Device testing, punch-flow edge cases, store review readiness | Part-time |
| DevOps | Mostly covered already (Azure, Cloudflare, Postgres in place); EAS handles mobile builds | Minimal |
| Project management | Jira board setup, ticket grooming, sprint planning | Shared |

# 8. Out of Scope for Phase 1 (Planned for Phase 2)

- Admin dashboard for managers (schedules, approvals, reports)

- Shift scheduling and swap requests

- Advanced pay rules (multi-rate, tips, bonuses)

- Geofenced clock-in restrictions

# 9. Assumptions

- Existing API and Azure/Cloudflare infrastructure remain available and stable

- Pay calculation business rules — including whether breaks are unpaid/deducted — are provided before backend build starts

- Apple Developer ($99/yr) and Google Play ($25 one-time) accounts are available for store submission

- Hours are estimates for planning; a fixed quote follows once mockups are approved